## Issue Log
Issue Log
Ask what is the issue preventing from happening. What is the decision or action that is needed to move forward
Issues
Ref | Domain | Issue name | Issue Description | Interdependencies | Impact | Raised by | Raised date | Closed date | Status | Owner | Action / Solution | Comment
1 |  | codes non fonctionnels ( sans hamming ) | Le code réception ne fonctionne pas. |  | High |  | 2025-02-03 | 2025-02-24 | Closed
2 |  | distance de 2m non atteinte (émission) | Le central node ne capte la lumière émise par le user node seulement à 90 cm. |  | Medium |  | 2025-02-03 |  | In Progress
3 |  | codes non fonctionnels ( avec hamming ) | Le code émission avec hamming ne fonctionne pas. |  | High |  | 2025-02-03 |  | In Progress
4 |  | Ensemble code + circuit ne fonctionne pas. | Les codes fonctionnent seulement indépendamment du circuit. |  | High |  | 2025-02-25 |  | In Progress
5 |  | problème avec code SEND | Le central node ne capte pas toujours le message SEND. |  | High |  | 2025-02-25 |  | In Progress
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Note on J5: Before closing the issue, the Project Manager must make a clear communication on the issue Action, Solution or Assumption to the person who raised the issue.

## Risk Log
Risk Log
Ask what the risk is, what causes the risk, and what are the measurable impacts the risk will have on the project
Risks
Ref | Domain | Risk name | Risk Description | Interdependencies | Raised by | Raised date | Closed date | Status | Owner | Mitigation action, if any | Last action date | Likelihood | Likelihood score | Impact | Impact score | Score | Comment
1 |  | changement de la personne qui présente la veille de la présentation | accident ou maladie |  |  | 2025-02-03 | [5 empty] | Low | 1 | High | 3 | 3
2 |  | composant circuit ne fonctionne pas le jour évaluation | composant cramé, … |  |  | 2025-02-03 | [5 empty] | Medium | 2 | High | 3 | 6
3 |  | perte du prototype |  |  |  | 2025-02-03 | [5 empty] | Low | 1 | High | 3 | 3
4 |  | Matériel au laboratoire | Bug du central node + pas assez de central nodes pour tous les groupes |  |  | 2025-02-20 | [5 empty] | High | 3 | Medium | 2 | 6
5 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
6 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
7 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
8 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
9 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
10 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
11 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
12 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
13 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
14 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
15 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
16 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
17 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
18 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
19 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
20 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
21 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
22 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
23 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
24 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
25 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
26 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
27 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
28 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
29 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
30 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
31 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
32 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
33 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
34 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
35 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
36 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
37 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
38 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
39 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
40 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
41 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
42 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
43 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
44 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
45 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
46 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
47 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
48 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
49 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
50 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
51 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
52 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
53 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
54 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
55 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
56 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
57 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
58 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
59 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
60 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
61 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
62 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
63 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
64 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
65 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
66 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
67 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
68 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
69 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
70 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
71 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
72 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
73 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
74 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
75 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
76 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
77 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
78 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
79 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
80 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
81 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
82 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
83 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
84 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
85 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
86 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
87 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
88 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
89 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
90 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
91 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
92 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
93 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
94 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
95 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
96 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
97 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
98 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
99 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
100 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
101 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
102 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
103 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
104 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
105 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
106 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
107 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
108 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
109 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
110 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
111 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
112 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
113 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
114 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
115 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
116 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
117 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
118 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
119 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
120 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
121 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
122 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
123 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
124 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
125 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
126 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
127 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
128 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
129 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
130 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
131 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
132 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
133 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
134 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
135 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
136 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
137 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
138 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
139 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
140 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
141 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
142 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
143 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
144 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
145 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
146 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
147 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
148 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
149 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
150 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
151 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
152 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
153 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
154 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
155 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
156 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
157 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
158 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
159 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
160 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
161 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
162 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
163 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
164 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
165 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
166 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
167 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
168 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
169 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
170 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
171 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
172 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
173 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
174 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
175 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
176 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
177 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
178 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
179 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
180 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
181 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
182 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
183 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
184 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
185 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
186 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
187 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
188 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
189 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
190 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
191 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
192 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
193 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
194 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
195 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
196 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
197 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
198 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
199 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
200 | [12 empty] | 0 |  | 0 | -1 | Input Likelihood & Impact
Note on I5: Before closing the risk the Project Manager must make a clear communication on the Mitigation action, if any, to the person who raised the issue.

## Instructions
Issue Instructions
Issues are classified by criticality in terms of their impact if not resolved
Decreases Revenue
| High | Causes Significant Increase in Costs (greater than 0.05% of revenue)
Significantly Disrupts Customer Relationship
Causes a Major Project Milestone to be Missed by more than a week
Slows Projected Revenue Growth
| Medium | Causes Minor Increase in Costs (less than 0.05% of revenue)
Causes Minor Disruption to Customer Relationship
Causes a Project Deadline to be Missed
Has Little/No Impact on Revenue
| Low | Has Little/No Impact on Costs
Has Little/No Impact on Customer Relationship
Has Little/No Impact on Meeting Project Deadlines
Risk Instructions
Risks are evaluated in terms of likelihood
| High | The risk is very likely to occur
| Medium | The risk may occur
| Low | The risk will most likely not occur
What is most important about risk occurrence is the measuring the impact.
| High | The risk occurrence will jeopardize the whole or a substantial part of the project
| Medium | The risk occurrence will have an impact on time, quality or cost elements of the project, and will alter the end deliverable
| Low | The risk occurrence can be resolved with reasonable effort, leaving the end deliverable unchanged
All risks do not need to be mitigated. The decision to mitigate a risk depends on the risk score
Reporting score
3 | 6 | 9 | Red | Big risk, need to mitigate urgently
2 | 4 | 6 | Amber | Risk needs to be mitigated
1 | 2 | 3 | Green | Can be mitigated

## Lists
Reference Lists
Here below are the lists used in the cell dropdown of the Risk and Issue logging tool. To modify those lists, simply change the cell values. To add values, insert a cell in the appropriated list. Additional changes can be made by using the "Insert\Name" menu from the toolbar.
Domain | Issue Status |  | Impact
… | New | Low | 1
… | In Progress | Medium | 2
… | Closed | High | 3
…
… | Risk Status |  | Risk Likelihood | Risk Impact
… | Open | Low | 1 | 1
General | Not Mitigated | Medium | 2 | 2
| Closed | High | 3 | 3